## SOP Document
SOP Standard Operating Procedure Document
Promotion Run and Timeline (C9MYR-RTN-SOP-B03)
Process name: | Promotion Run and Timeline | Version number: | V1.0
Department: | VIP Retention | Effective date:
Process owner: | VIP Retention / ATL | Approved by:
Step no. | Step name | Specific action | Operating standard | Tools / forms used | Points to note
1 | Assign Promo Owner + Announcer | On deciding to run a promotion: name one Promo Owner and one Announcer. | One person handles the whole promotion; one person announces. Role titles only. Never split ownership. | Lark
2 | Prepare the plan + approval | Phase 1 (T-7 to T-5): draft window (hard start + end), brands, tiers, bonus, platform split, content scope; get ATL / Supervisor sign-off. | Nothing is built until approved. Hard end date required. | Proposal doc, Lark
3 | Build content + bonus rule | After approval: content per brand x language (Push SOP 34); bonus ladder, cap, turnover, validity via Bonus SOP (23). | Approval gate applied. No new ladder outside the Bonus SOP. | Templates, Push SOP, Bonus SOP
4 | Brief the team | Phase 2 (T-3 to T-2): brief all CS on the promotion, eligibility, channel actions and the timeline. | Confirm everyone understands their part before go-live. | Briefing, Lark
5 | Announce + go live | Phase 3 (T-0): Announcer makes one announcement; banners and content live. | Single announcement point. Issue only within the window. | BO, Lark
6 | Execute CS actions | Phase 4 (during): send per channel; contact before deposit; tag per promotion; log QA with a BO screenshot. | RG / chase flag excluded, route to welfare. Contact precedes deposit. | BO, QA Record (12)
7 | Follow up daily | Phase 5 (during): track take-up, ROI and abuse; chase pending; escalate to ATL. | Watch concentration and abuse. | QA Record, ROI Table (14)
8 | Tear down + review | Phase 6 (T+1 to T+3): expire banners, close tags; post-promotion review result vs target; feed lessons back. | Banner self-drops at window end; never Never-Expires. | BO, ROI Table, review doc
Core four parts of an SOP
1. Action (what to do) 2. Order (what comes first, next) 3. Standard (how well) 4. Tools (what to use)
Optimised flow chart
Flow shown below. Drawn in Lark flowchart or Draw.io for the live SOP.
Roles (one each per promotion)
Role | Responsibility
Promo Owner | Handles the promotion end to end: prepare, brief, follow up, review
Announcer | Makes the single go-live announcement; sets the promotion live
VIP CS | Execute: send per channel, contact before deposit, tag, log QA
ATL / Supervisor | Approve the plan and budget before any build
Promotion timeline (lead times proposed, confirm with ATL)
Phase | When (proposed) | Who
1 Prepare | T-7 to T-5 | Promo Owner
2 Brief the team | T-3 to T-2 | Promo Owner
3 Start (announce) | T-0 | Announcer
4 CS actions | During window | VIP CS
5 Follow up | Daily during | Promo Owner
6 Review | T+1 to T+3 | Promo Owner
Lead times are PROPOSED, not locked: confirm the exact days with the ATL. This SOP is the timeline + ownership wrapper; Weekend Campaign (15) and Special Event Campaign (35) hold the component detail. FIFA layout is a format reference only; do not import cross-team promotion context.